## Sheet1
SEVERITY
| Risk | Evaluation | Response | Control Measures | Likelihood | Impact | Risk Level | Date Added |  |  | Minimal | Minor | Moderate | Major | Severe
1 | May not hit deadline target | App won't be ready to demo and I will miss out on a higher score | Focus only on the MVP. Anything else is irrelevant if it's not finished on time | Plan for MVP to be realistically achievable | possible | Severe | 10 | 17/05/2021 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Complex Architecture | I could struggle to figure out what is causing a bug | Use automated testing to figure out where things are going wrong | Try to simplify the database structure. Minimise tables, minimise relationships. | Expected | Major | 16 | 17/05/2021 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Missuse of version control | Pushing broken code and overwriting main could destroy hours of work | Browse historic commits on GitHub and choose previous version | Add passwords to protect myself from myself merging things in the wrong branch. Stick to dev branch until Im sure its bug free. | Possible | Minor | 6 | 17/05/2021 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Database could get hacked | All inputted data could be lost | Create new database and sync it. Uplaod backup data to new DB | Store backup data offline. | Unlikely | Moderate | 3 | 17/05/2021 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | Illness | I might struggle to work as fast, or at all | I would have to let one of the tutor know that I am unwell. I would then have to carry on anyway and just get it done. | Live a healthy lifestyle. Don't get to close to those pesky customers at Sainsburys | Possible | Moderate | 6 | 17/05/2021 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Computer could breakdown | I wouldn't be able to do any work | Source a new laptop | Always have a backup PC | Unlikely | major | 4 | 17/05/2021
7 | GCP could go down | I wouldn't be able to connect my cloud based database or host the webapp on a VM. | Pray it goes back online | Aways have a contigency plan to use another online web services provider, just in case. | Unlikely | Severe | 5 | 17/05/2021
8 | I could forget Jenkins password | I won't be able to run the app via Jenkins | Setup a new VM with Jenkins | Either write down the password, choose one that can be easily remembered or use a password manager. | Possible | Major | 8 | 21/05/2021
9 | Unable to get relationship working in database | The relationship with the player and the position won't work which is part of the MVP | Keep trying to get it working | Go through past demos & QA Community | likely | Major | 12 | 22/05/2021
10 | Firewall may not allow VM to access database. | App won't run through VM or Jenkins | Change connections in MySql database on GCP to allow IP address of VM | Allow this straight away once setup of VM is complete | Guarenteed (if not setup) | Severe | 25 | 22/05/2021